## Kanban
Team 46: Smart SKU storage | https://github.com/users/04Maksimka/projects/5
IW-2026 Team kanban sheets: Cohort SALIMON (Materials & Devices)
| PROBLEM = CustDev |  | SOLUTION = Science |  | PROTOTYPE = Technology |  | VISION and GANTT for the next iteration
What we learned so far | B2B focus confirmed via ~60 cold calls to manufacturing and assembly facilities yielding ~9% interest and 3 companies formally agreeing to September on-site prototype testing; B2C deferred due to higher acquisition friction and misalignment with core inventory-loss value proposition. |  | Weight-based counting validated by external studies (load-cell stock study 2025, mean error 0.24 g; Cal Poly 2015); reliable counting requires scale noise < 50% of single unit weight. | Viktor, Maksim | Base block = 4 weighing bins + ESP32, NFC tag per bin; blocks stack via pogo-pin connectors (power + data) on all sides; BOM per block: 1,915–3,079 ₽ (local fast sourcing chosen for Sept 18 deadline). | Artem, Andrey | Roles split, custdev assigned to Viktor and Maksim; market draft: TAM = 790M ₽/yr, ACV 90k ₽ (assumption to be validated).
What we plan to do | Glazov furniture factory; University FabLabs (HSE, MIPT) to validate NFC bin-recalibration when students relocate bins; Fastener suppliers (Taflor); ATV manufacturer (Russkaya Mekhanika, Vologda); Conveyor assembly (Sdelay Zavod); Generalized sectors (Bag & apparel); Goal: validate 90k ₽ ACV and secure floor access for authentic promo filming. | Varya, Viktor, Maksim | Bench-test load cell + HX711 accuracy on real fasteners; define minimal honest unit weight (drives final sensor choice). | Artem, Andrey | Finalize connection architecture (SmartSKU #1); buy electronics (SmartSKU #2): I/O port expander, 7-segment display, RFID reader, RFID tags, optional expansion board, plus base ESP32, HX711, 1kg load cells, pogo-pins (local fast delivery via Ozon); box model + CAD 3D printing (SmartSKU #3); assemble and test "it weighs, it counts" prototype by Sept 18. | Artem, Andrey | Promo video and slides for customers (SmartSKU #4); promo presentation (SmartSKU #6); Osterwalder + Gantt supplementary slide (pending team input); validate the 90k ₽ ACV in custdev calls. | Varya
What are the challenges | Video/slides: how to get physical access to the manufacturing floor for authentic filming; articulating "time-saving" value proposition without buzzwords (focusing on metrics like "40 mins/day saved on M1.6-M3 counting"); tracking and accumulating data on inventory losses. | Varya, Maksim, Viktor | Drift and vibration filtering for load cells; parts lighter than ~0.3 g may require a better sensor/ADC. | Andrey | Per-bin digital displays: finalize type (LED digits vs e-ink) and cost; max blocks per tower limited by power and data bus; CRITICAL: everything must weigh and count by Sept 18. | Artem, Andrey | Evolution pillar is 20% of the grade — keep the idea-selection story ready for Q&A (Slide 19); prepare clear differentiation vs Bossard SmartBin (autonomous, NFC recalibration, 1C integration).